## WBS
WBS
Item (WBS) Number | Task Name | Duration (Hours)
1 | Transfering Data | 24
1.1 | Preparation | 7
1.2 | Setting up Cloud Server | 5
1.3 | Configuring the cloud server | 6
1.4 | Backing up and Transfering all files and information from local server | 6
2 | Remove reliance | 15
2.1 | Assessment of all services dependent on Active Directry and identifying alternatives | 5
2.2 | Removing user data from active directory and replicating the file shares and permission to cloud based solution | 10
3 | Automatic Change Identification | 26
3.1 | Identifying the solution to track live document changes | 7
3.2 | Planning the solution implementation | 10
3.3 | Implementing the solution | 9
4 | Hand over Documentation | 5
4.1 | Create documentation and share documentation | 5
| Complete Number of Hours | 140

## Selected Services
Selected Services
Requirements | Selected Service | Explanation | Cost (AUD)
Cloud Based Server Database | Oracle Database | Scalable, high-performance, secure cloud-based database solution | 5000
Cloud Based Server Storage | OneDrive | Microsoft's cloud storage solution offering seamless integration with Windows 10 and Microsoft 365. | 140
Virtual Meetings Ecosystem | Teams | Reliable platform for virtual meetings and collaboration
Live document collaboration Ecosystem | Microsoft 365 | Comprehensive suite for real-time document collaboration, including Word, Excel, and PowerPoint.
Suitable OS Solution | Windows 10 | Modern operating system offering security, productivity, and compatibility. | 150
|  | Upfront Costs | 5290
|  | Ongoing Costs per month | 20

## Employee Database
Employee Database
Employee Group | Leasing Rate P/H
- | -
Tanisha Sharma | 100
Benafsha Nabawi | 95
Taiba Safari | 95
Tanisha Sharma + Benafsha Nabawi | 195
Tanisha Sharma + Taiba Safari | 195
Benafsha Nabawi + Taiba Safari | 190
All Employees | 290

## GANTT Chart
GANTT Chart
| Upgrading Networking Infrastructure to a Cloud-based Solution |  |  | Small ICT Company
| 2024-04-01 |  |  | 2024-04-22
WBS Number | Dependency | Control Account/Work Package | Assigned Employee Group |  | Start Date | End Date | Duration (Hours)
[8 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
[8 empty] | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2024-09-30
1 | none | Transfering Data | Tanisha Sharma + Taiba Safari |  | 2024-04-01 | 2024-04-05
1.1 | none | Preparation | Tanisha Sharma |  | 2024-04-01 | 2024-04-01 | 7
1.2 | 1.1 | Setting up Cloud Server | Taiba Safari |  | 2024-04-02 | 2024-04-02 | 5
1.3 | 1.2 | Configuring the cloud server | Taiba Safari |  | 2024-04-03 | 2024-04-03 | 6
1.4 | 1.3 | Backing up and Transfering all files and information from local server | Tanisha Sharma + Taiba Safari |  | 2024-04-04 | 2024-04-05 | 6
2 | 1 | Remove reliance | Tanisha Sharma + Benafsha Nabawi |  | 2024-04-08 | 2024-04-11
2.1 | 1.4 | Assessment of all services dependent on Active Directry and identifying alternatives | Tanisha Sharma + Benafsha Nabawi |  | 2024-04-08 | 2024-04-08 | 5
2.2 | 2.1 | Removing user data from active directory and replicating the file shares and permission to cloud based solution | Benafsha Nabawi |  | 2024-04-09 | 2024-04-11 | 10
3 | 2 | Automatic Change Identification | Benafsha Nabawi + Taiba Safari |  | 2024-04-15 | 2024-04-19
3.1 | 2.2 | Identifying the solution to track live document changes | Benafsha Nabawi |  | 2024-04-15 | 2024-04-15 | 7
3.2 | 3.1 | Planning the solution implementation | Taiba Safari |  | 2024-04-16 | 2024-04-17 | 10
3.3 | 3.2 | Implementing the solution | Benafsha Nabawi |  | 2024-04-18 | 2024-04-19 | 9
4 | 3 | Hand over Documentation | All Employees |  | 2024-04-22 | 2024-04-22
4.1 | 3.3 | Create documentation and share documentation | All Employees |  | 2024-04-22 | 2024-04-22 | 5
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-

## Staffing Budget
Staff Budget Breakdown
Number of Work Hours | Control Account/Work Package | Employee Group | Per Hour Cost | Line Total
7 | Preparation | Tanisha Sharma | 100 | 700
5 | Setting up Cloud Server | Taiba Safari | 95 | 475
6 | Configuring the cloud server | Taiba Safari | 95 | 570
6 | Backing up and Transfering all files and information from local server | Tanisha Sharma + Taiba Safari | 195 | 1170
0 | Remove reliance | Tanisha Sharma + Benafsha Nabawi | 195
5 | Assessment of all services dependent on Active Directry and identifying alternatives | Tanisha Sharma + Benafsha Nabawi | 195 | 975
10 | Removing user data from active directory and replicating the file shares and permission to cloud based solution | Benafsha Nabawi | 95 | 950
0 | Automatic Change Identification | Benafsha Nabawi + Taiba Safari | 190
7 | Identifying the solution to track live document changes | Benafsha Nabawi | 95 | 665
10 | Planning the solution implementation | Taiba Safari | 95 | 950
9 | Implementing the solution | Benafsha Nabawi | 95 | 855
0 | Hand over Documentation | All Employees | 290
5 | Create documentation and share documentation | All Employees | 290 | 1450
8760
|  |  | Subtotal | 17520
|  |  | GST | 10%
|  |  | Total | 19272